## Cover
TEST PLAN
Project Name | Lazada Testing |  |  | Reviewer | Võ Hoàng Nhi, Đoàn Nhất Linh
Project Code | LT01 |  |  | Review date | 2024-10-30
Creator | Nguyễn Phương Nhã, Đoàn Quốc Đăng |  |  | Approver | Nguyễn Tấn Khoa
Version | v1.0 |  |  | Approval Date | 2024-10-31
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
26/10/2024 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
Lazada SRS |  |  |  | 0.5
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
| # | Items | Note
1
2
Quality metric
Description of target
| # | Items | Target | Note
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80%
| 3 | Software is correct with SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan |  |  | Leader / Testers
2 | Create test design |  |  | Tester
3 | Create test cases |  |  | Tester
4 | Create test data |  |  | Teseter
5 | Execute system test |  |  | Teseter
6 | Defects list |  |  | Teseter
7 | Create test report |  |  | Leader / Testers
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 26/10/2024 | Test leader | Test manager, Team | This document itself
2 | Test cases | 26/10/2024 | Test leader | Test manager, Team
3 | Defect logs | 26/10/2024 | Test leader | Test manager, Team
4 | Test report | 26/10/2024 | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on E32: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G32: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B41: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
Các tính năng chính của Lazada được mô tả ở tài liệu SRS được thực hiện test theo độ ưu tiên từ cao đến thấp (Cao thực hiện trước và thấp thực hiện test sau). |  | Lazada_SRS_V0.5
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop
OS | Window 10 64-bit
Software | Chrome version 130.0.6723.70 Edge 131.0.2903.14
Database | MySQL
Browser | Microsoft Edge, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 21130079_Nguyễn Tấn Khoa | Leader | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Quản lý Giỏ hàng, Áp dụng Mã giảm giá.
2 | 21130014_Đoàn Quốc Đăng | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho Quản lý tài khoản, Hồ sơ tài khoản, Sổ địa chỉ, Tùy chọn thanh toán
3 | 21130091_Đoàn Nhất Linh | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng đánh giá sản phẩm, sản phẩm yêu thích và gian hàng đang theo dõi.
4 | 21130122_Nguyễn Phương Nhã | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Đặt hàng, Thanh toán, Hủy đơn hàng
5 | 21130126_Võ Hoàng Nhi | Member | - Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Kế toán -> Phí quản lí -> DS invocie
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2024-10-26 | 2024-10-28
2 | Create test design | 2024-10-29 | 2024-11-01
3 | Create test case | 2024-11-02 | 2024-11-08
4 | Execute test and log bugs | 2024-11-09 | 2024-11-15
5 | Evaluting exit criteria & Test report | 2024-11-16 | 2024-11-22
6 | Review | 2024-11-23 | 2024-11-29
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 2
| Create test design | 2 | 3
| Create test case | 5 | 6
| Execute test and log bugs | 11 | 6
| Evaluting exit criteria & Test report | 17 | 6
| Review | 23 | 7
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | October | [5 empty] | November
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Create test plan | Team | bar: October 26 to October 28
2 | Create test design | bar: October 29 to November 1
2.1 | Danh sách sau quân sự | 21130079_Nguyễn Tấn Khoa | bar: October 29 to October 31
2.2 | Đánh giá sản phẩm, sản phẩm yêu thích và gian hàng đang theo dõi | 21130091_Đoàn Nhất Linh | bar: October 29 to October 31
2.3 | Danh sách đang học quân sự | 21130014_Đoàn Quốc Đăng | bar: October 29 to October 31
2.4 | Đặt hàng, hủy hàng, thanh toán | 21130122_Nguyễn Phương Nhã | bar: October 29 to October 31
2.5 | Kế toán -> Phí quản lí -> DS invocie | 21130126_Võ Hoàng Nhi | bar: October 29 to October 31
2.6 | Review | Team | bar: November 1
3 | Create test case | bar: November 2 to November 8
3.1 | Danh sách sau quân sự | 21130079_Nguyễn Tấn Khoa | bar: November 2 to November 6
3.2 | Đánh giá sản phẩm, sản phẩm yêu thích và gian hàng đang theo dõi | 21130091_Đoàn Nhất Linh | bar: November 2 to November 6
3.3 | Danh sách đang học quân sự | 21130014_Đoàn Quốc Đăng | bar: November 2 to November 6
3.4 | Đặt hàng, hủy hàng, thanh toán | 21130122_Nguyễn Phương Nhã | bar: November 2 to November 6
3.5 | Kế toán -> Phí quản lí -> DS invocie | 21130126_Võ Hoàng Nhi | bar: November 2 to November 6
3.6 | Review | Team | bar: November 7 to November 8
4 | Execute test and logs bug | bar: November 9 to November 15
4.1 | Danh sách sau quân sự | 21130079_Nguyễn Tấn Khoa | bar: November 9 to November 13
4.2 | Đánh giá sản phẩm, sản phẩm yêu thích và gian hàng đang theo dõi | 21130091_Đoàn Nhất Linh | bar: November 9 to November 13
4.3 | Danh sách đang học quân sự | 21130014_Đoàn Quốc Đăng | bar: November 9 to November 13
4.4 | Đặt hàng, hủy hàng, thanh toán | 21130122_Nguyễn Phương Nhã | bar: November 9 to November 13
4.5 | Kế toán -> Phí quản lí -> DS invocie | 21130126_Võ Hoàng Nhi | bar: November 9 to November 13
4.6 | Review | Team | bar: November 14 to November 15
5 | Evaluting exit criteria & Test report | Team | bar: November 16 to November 22
6 | Review | Team | bar: November 23 to November 29

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
1 | 21130079_Nguyễn Tấn Khoa
2 | 21130014_Đoàn Quốc Đăng
3 | 21130091_Đoàn Nhất Linh
4 | 21130122_Nguyễn Phương Nhã
5 | 21130126_Võ Hoàng Nhi